viii)     Head-wise break-up of expenditure	:

Annexure -I

## TABLE 2 : HEADWISE BREAK-UP OF EXPENDITURE (C-MET)

(Rs. Lakhs)

| S l | Head | Approved Budget Outlay | Actual Grant Received | Expenditure incurred Upto 28.02.2025 Rs. FE Total |  |  | Anticipated BE Expenditure from 01.03.2025 to 31.03.2025 Rs. FE Total |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Capital Equipment (FE | 30.00 | 30.00 | 23.85257 |  | 23.85257 | 6.20 |  | 6.20 | Total received 107.03160lakh s, Returned to CNA 20 lakhs. Total effective grant received 87.0316 Lakhs. Request for release of 35 lakhs up to 31.03.2026 |
|  | component) * |  |  |  |  |  |  |  |  |  |
| 2 | Consumable items (FE | 30.00 | 20.00 | 14.46611 |  | 14.46611 | 7.4982 |  | 7.4982 |  |
|  | component) |  |  |  |  |  |  |  |  |  |
| 3 | Duty on Imports | -- | -- | -- |  | -- | -- |  | -- |  |
| 4 | Staff salaries | 62.3076 | 20.3256 | 17.75342 |  | 17.75342 | 1.2980 |  | 1.2980 |  |
| 5 | Travel | 4.00 | 3.00 | 0.44824 |  | 0.44824 | -- |  | -- |  |
| 6 | Contingencies | 12.00 | 8.00 | 6.10225 |  | 6.10225 | 6.52502 |  | 6.52502 |  |
| 7 | Overheads, if any | 8.665 | 5.706 | 2.893 |  | 2.893 | -- |  | -- |  |
| 8 | Other expenditure | -- | -- | -- |  | -- | -- |  | -- |  |
|  | debitable to this project |  |  |  |  |  |  |  |  |  |
|  | (please specify) |  |  |  |  |  |  |  |  |  |
|  | Total | 146.9726 | 87.0316 | 65.513174 |  | 65.513174 | 21.52122 |  | 21.52122 |  |

- FE utilized, over and above sanction made by DIT, through OGL facilities may be indicated separately.

- Please indicate if there is any deviation from originally approved budget and whether necessary approval has been taken.